# Digitalized Daily Progress Report (DPR)

Comprehensive User & Operational Manual

# 1. What is Digitalized DPR?

DPR stands for Daily Progress Report. In the context of large-scale projects, it is the primary record of all physical work, manpower utilization, and material usage completed on a project site within a 24-hour period.

## Why Digitalize?

Traditional manual reporting is prone to delays, data silos, and transcription errors. The Digitalized DPR system solves these issues through:

Real-Time Data Entry: Field supervisors enter data directly on the platform.

Seamless Validation: Site PMs review entries with cell-level feedback.

Direct P6 Integration: Validated data is pushed directly to Oracle P6, eliminating double entry.

Centralized Audit Trail: Every change, comment, and approval is tracked.

# 2. User Roles & Workflows

## Supervisor (The Field Expert)

Supervisors are the foundation of the data. They record today's achievements against yesterday's benchmarks.

Key Tasks:

Select Project & Sync: Ensure the activity list is up-to-date from the P6 database.

Data Entry: Navigate through various sheet tabs (DP Qty, Manpower, etc.) to record progress.

Submission: Submit completed sheets for PM review.

## Site PM (The Validator)

Site Project Managers act as the quality gates, ensuring data accuracy before it moves to project controls.

Key Tasks:

Dashboard Monitoring: View pending submissions from all site supervisors.

Detailed Review: Use cell-level comments to request specific corrections.

Approval: Confirm accuracy and send the sheet to the PMAG team.

## PMAG (Project Management AG)

PMAG oversees the entire project data lifecycle and manages the interface with scheduling tools like Oracle P6.

Key Tasks:

Final Review: A secondary check to ensure global project standards.

Push to P6: The click of a button that updates the project schedule with real-world data.

# 3. Understanding the Reporting Sheets

## DP Qty (Daily Progress Quantity)

Captures the physical work done (e.g., Cubic Meters of concrete, count of piles). It tracks 'Today Achievement' and automatically calculates 'Cumulative Progress' and 'Balance Scope'.

## Manpower Details

Critical for resource monitoring. Tracks direct and indirect labor counts by contractor and site section.

## Vendor Block/IDT

Tracks specific vendor performance and the movement of Internal Delivery Tokens (IDT) for material procurement.

# 4. Common Usage Scenarios

## Scenario: Handling a Rejected Sheet

If a PM rejects your sheet, it will reappear in your 'Supervisor Dashboard' with a 'Rejected' status. Open the sheet to see red markers on specific cells. Hover over or click these cells to see the review comments. Correct the data and resubmit immediately.

## Scenario: Editing Past Data

Data accuracy is paramount. If you need to edit a previous day's report, select the date. The system will require a 'Business Reason' for the modification, which will be logged for PM review.

Digitalized DPR System - Ensuring Data-Driven Project Excellence.